## Sheet1
|  |  | Total | Total | Total | Total | Total | Total
Team: | Team_04 |  | original | remaining | total | effort spent by | effort spent by | effort spent by
Milestone: | M2 |  | estimated effort | estimated effort | effort spent | <lowest-class-id> | <middle-class-id> | <highest-class-id>
Week Ending: | 2018-03-20 |  | (person hours) | (person hours) | (person hours) | (person hours) | (person hours) | (person hours)
|  |  |  | 20 | 15 | 15 | 0 | 0
effort spent
Task # | Task Name | Task Description | original | remaining | total | effort spent by | effort spent by | effort spent by | estimated | Start-Date | Completion Date
|  |  | estimated effort | estimated effort | effort spent | <lowest-class-id> | <middle-class-id> | <highest-class-id> | percent | yyyy/mm/dd | yyyy/mm/dd
|  |  | (person hours) | (person hours) | (person hours) | (person hours) | (person hours) | (person hours) | complete | or N/A | or N/A
1 | IDD Preparation | IDD Prerparation for the dimension | 40 | 20 | 15 | 15 | 0 | 0 | 65% | 2018-03-07 | N/A
Note on E1: Author: Automatically calculated
Note on F1: Author: Automatically calculated
Note on G1: Author: Automatically calculated
Note on H1: Author: Automatically calculated
Note on I1: Author: Automatically calculated
Note on J1: Author: Automatically calculated
Note on E7: Author: Use only integer hours to enter the estimated effort when you first added the task
Note on F7: Author: Initially the same as original effort, as work progresses adjust to reflect current estimate for effort remaining.
Note on G7: Author: Automatically calculated
Note on H7: Author: This is for the team member who's class-id starts with the lowest number. For each task, enter number hours spent this week as an integer or zero if none spent.
Note on I7: Author: This is for the team member who's class-id starts with the second-lowest number. For each task, enter number hours spent this week as an integer or zero if none spent.
Note on J7: Author: This is for the team member who's class-id starts with the third-lowest number. For each task, enter number hours spent this week as an integer or zero if none spent.
Note on K7: Author: Enter as an integer between 0 and 100 as the current estimate for percent done. This is based on progress towards completion of the task -- not based on original estimated effort, remaining estimated effort or spent effort.