## Sheet1
Serial No. | Project Milestone | Task | Resources Assigned | Hours worked-6Feb-12Feb | Hours worked-13Feb-19Feb
1 | M1 | Create GIT repository | 2700-Indu | 0.25
1.01 | M1 | Create Project Plan | 2700-Indu |  | 1
1.02 | M1 | Create Change Log | 2700-Indu |  | 1
1.03 | M1 | Research Tools | 2100-Prerana |  | 2
1.04 | M1 | Set up Slack Acct | 2100-Prerana |  | 0.25
1.05 | M1 | Milestone 1 Deliverable 1 | 2700-Indu |  | 1
1.06 | M1 | Milestone 1 Deliverable 2 | 2700-Indu |  | 1
1.07 | M1 | Milestone 1 Deliverable 3 | 2100-Prerana | 0.25 | 0.25
1.08 | M1 | Milestone 1 Deliverable 4 | 2100-Prerana | 0.1 | 0.9
1.09 | M1 | Milestone 1 Deliverable 5 | 2100-Prerana |  | 0.2
1.1 | M1 | Day wise reports | 2100-Prerana |  | 0.1
1.11 | M1 | Submiting M1 on BB | 2100-Prerana |  | 0.25